## Slide 1
Briefing on strategic programming
Ankara, Turkey
26th of February 2020
Workplan
for Black Sea Basin programming

## Slide 2
Main steps 1/3
  nominations
  1st JPC meeting approving:
  Rules of Procedures
  continuity of current MA
  Workplan
Setting up
the Joint Programming Committee
Collection & analysis of statistical data
  territorial analysis & SWOT analysis of eligible area
  identification of joint investment needs
  stakeholders’ consultations
Territorial analysis
Nov 2019 - Jan 2020 Feb - Mar 2020 Apr - Sept 2020
  selecting data set series
  template design
  collecting data from NAs
  trend analysis
Notes: Type of activity
Date of finalization
Selecting indicators for the territorial analysis:
Identification of information sources, period of analysis, and methodology
13.02.2020
Distribution tasks between national experts
14.02.2020
Template design for the data collection
14.02.2020
Sending templates to MA with open data inserted
21.02.2020
MA sends semi-filled-in templates to NAs
24.02.2020
Collecting templates from NA
06.03.2020
Trend analysis draft
20.03.2020

## Slide 3
Main steps 2/3
strategy
priorities
financing plan
partners' involvement
communication & visibility
implementation
Drafting
the operational programme
Strategic Environmental Assessment (SEA)
  consultation on the last draft
  final version
  approval by participating countries
Revision
of the operational programme
Oct 2020 - Feb 2021 Jan - Feb 2021 Mar - May 2021
  preparation of SEA

## Slide 4
Main steps 3/3
Max 6 months after Max 6 months after Max 3 months after Max 31 Dec of the year following Multi-annual strategy document JOP submission JOP approval the year with 1st budget commitment
Submission
of the operational programme
to EC
Negotiations & approval of the operational programme
by EC
Setting up
the Monitoring Committee & Group of Auditors
Signature
of Financing Agreements

## Slide 5
Set-up of national working groups
Programming process:
generally coordinated at national level,
however involvement of actors from the regional and local level is highly recommended.
Nevertheless, limited number of JPC members in order to allow efficient discussion and decision–making process.
National working groups on programming:
to be set-up at each country level,
multi-level partnership,
for carrying out consultations throughout programming process (during events or written consultations).
JPC remains the decision-making body.

## Slide 6
Questions?

## Slide 7
Our goal:
Timely programming as to ensure efficient usage of funds
Further information:
www.blacksea-cbc.net
www.facebook.com/BlackSeaBasin
Managing Authority
blacksea-cbc@mlpda.ro